## Task Board
Maxi Health — Development Task Board
Stack: Next.js 14 · TypeScript · Tailwind · Prisma/SQLite · Zustand · Nodemailer
ID | Phase | Task | Description | Priority | Est. Hours | Depends On | Status | Notes
Phase 1 - Scaffold
1.1 | 1 - Scaffold | Create Next.js app | Run create-next-app in 'maxi helth/' with TypeScript, Tailwind CSS, App Router enabled | High | 1 | - | Pending
1.2 | 1 - Scaffold | Install all dependencies | npm install: prisma, @prisma/client, zustand, react-hook-form, zod, nodemailer, @types/nodemailer | High | 0.5 | 1.1 | Pending
1.3 | 1 - Scaffold | Configure TypeScript strict mode | Set strict: true in tsconfig.json. No any types allowed. | High | 0.5 | 1.1 | Pending
1.4 | 1 - Scaffold | Create .env and .env.example | Define DATABASE_URL, OWNER_EMAIL, GMAIL_USER, GMAIL_APP_PASSWORD, ADMIN_PASSWORD. Add .env to .gitignore. | High | 0.5 | 1.1 | Pending
Phase 2 - Database
2.1 | 2 - Database | Write Prisma schema | Models: Product, Order, OrderItem with all relations. | High | 1 | 1.2 | Pending | SQLite provider
2.2 | 2 - Database | Run initial migration | npx prisma migrate dev --name init. Generates dev.db and migration SQL. | High | 0.5 | 2.1 | Pending
2.3 | 2 - Database | Write and run seed file | seed.ts: 8-10 sample vitamins (Vitamin C, Omega-3, Vitamin D3, Zinc, Magnesium...) with prices, slugs, images. | Medium | 1 | 2.2 | Pending | Placeholder images
Phase 3 - Lib
3.1 | 3 - Lib | src/lib/prisma.ts | Singleton PrismaClient - prevents multiple instances during Next.js hot reload. | High | 0.5 | 2.2 | Pending
3.2 | 3 - Lib | src/lib/env.ts | Validate all required env vars at startup with zod. App throws a clear error if any are missing. | High | 0.5 | 1.4 | Pending | Fail fast at boot
3.3 | 3 - Lib | src/lib/email.ts | sendOrderNotification(order): Nodemailer + Gmail SMTP. Sends formatted HTML email to OWNER_EMAIL. | High | 1.5 | 3.2 | Pending | Needs Gmail App Password
Phase 4 - API Routes
4.1 | 4 - API Routes | GET /api/products | Return all products from DB. Optional ?category= query param filter. | High | 1 | 3.1 | Pending
4.2 | 4 - API Routes | GET /api/products/[id] | Return single product by id. 404 if not found. | Medium | 0.5 | 4.1 | Pending
4.3 | 4 - API Routes | POST /api/orders | Validate body with zod. Insert Order + OrderItems. Generate reference MH-XXXXX. Call sendOrderNotification(). | High | 2 | 3.3 | Pending | Core business logic
4.4 | 4 - API Routes | GET /api/orders/[id] | Customer order lookup by reference number. | Medium | 0.5 | 4.3 | Pending
4.5 | 4 - API Routes | Admin: GET /api/admin/orders | Return all orders newest-first. Protected by admin cookie middleware. | High | 1 | 3.1 | Pending
4.6 | 4 - API Routes | Admin: PATCH /api/admin/orders/[id] | Update order status (PENDING / PROCESSING / DELIVERED / CANCELLED). Zod-validated body. | High | 1 | 4.5 | Pending
4.7 | 4 - API Routes | Admin: POST /api/admin/login | Compare password vs ADMIN_PASSWORD env var. Set HttpOnly session cookie on success. | High | 1 | 3.2 | Pending
4.8 | 4 - API Routes | Admin: POST /api/admin/logout | Clear the admin session cookie. | Medium | 0.5 | 4.7 | Pending
4.9 | 4 - API Routes | src/middleware.ts - admin guard | Check HttpOnly cookie on /admin/* and /api/admin/* routes. Redirect to /admin login if missing. | High | 1 | 4.7 | Pending
Phase 5 - Components
5.1 | 5 - Components | src/store/cartStore.ts | Zustand store: items[], addItem, removeItem, updateQty, clearCart. Persisted to localStorage. | High | 1.5 | 1.2 | Pending
5.2 | 5 - Components | Navbar.tsx | Logo, nav links, cart icon with item count badge. Mobile hamburger menu. | High | 1.5 | 5.1 | Pending | Mobile-first
5.3 | 5 - Components | ProductCard.tsx | Product image (Next.js Image), name, category badge, price, Add to Cart button. | High | 1 | 5.1 | Pending
5.4 | 5 - Components | CartItem.tsx | Row: product image, name, unit price, qty +/- controls, remove button, line total. | High | 1 | 5.1 | Pending
5.5 | 5 - Components | CheckoutForm.tsx | Fields: name, phone, address, notes. react-hook-form + zod schema. Submit calls POST /api/orders. | High | 2 | 5.1 | Pending
Phase 6 - Customer Pages
6.1 | 6 - Customer Pages | Home page / | Hero banner + product grid with ProductCard. Category filter tabs. 1-col mobile to 3-col desktop. | High | 2 | 5.3 | Pending | Mobile-first
6.2 | 6 - Customer Pages | /products/[id] | Product image, full description, price, stock, Add to Cart, Back link. | High | 1.5 | 5.3 | Pending
6.3 | 6 - Customer Pages | /cart | Cart items list, subtotal, Continue Shopping and Proceed to Checkout buttons. Empty cart state. | High | 1.5 | 5.4 | Pending
6.4 | 6 - Customer Pages | /checkout | Order summary + CheckoutForm. On success: redirect to /order-confirmed?ref=MH-XXXXX. | High | 2 | 5.5 | Pending
6.5 | 6 - Customer Pages | /order-confirmed | Thank-you message, order reference number, Continue Shopping CTA. | Medium | 0.5 | 6.4 | Pending
Phase 7 - Admin Pages
7.1 | 7 - Admin Pages | /admin - login page | Password form. POST to /api/admin/login. Redirect to /admin/orders on success. | High | 1 | 4.7 | Pending
7.2 | 7 - Admin Pages | /admin/orders - order list | Table: reference, customer, phone, total, status badge, date, View link. Status filter. | High | 2 | 4.5 | Pending
7.3 | 7 - Admin Pages | /admin/orders/[id] - detail | Full order info, items table, status dropdown. PATCH on status change. | High | 2 | 4.6 | Pending
Phase 8 - Polish
8.1 | 8 - Polish | Mobile-first responsive audit | Test all pages at 375px, 768px, 1280px. Fix layout issues. | High | 2 | 6.5, 7.3 | Pending
8.2 | 8 - Polish | End-to-end order flow test | Browse -> cart -> checkout -> confirm -> check owner email -> admin status update. | High | 1 | 8.1 | Pending
8.3 | 8 - Polish | Loading and error states | Loading spinners on form submit buttons. User-friendly error messages on API failures. | Medium | 1.5 | 6.4 | Pending
8.4 | 8 - Polish | SEO metadata | Add Next.js metadata (title, description) for home and product detail pages. | Low | 0.5 | 6.2 | Pending
Total: 36 tasks